## Slide 1
SPEAK
Language-Learning Platform for Primary-School Children
Project Status, Feasibility
and Delivery Plan
Janaki Badu · Full-Stack Web Developer Companion to the SRS (07 Jul 2026) and the Software Design Document (11 Jul 2026)
Notes: Welcome. Today is a status and planning meeting, not a demo. We have finished requirements and design; I want to show you exactly what is built, what is left, how long it will take at six hours a week, and give you a straight answer on recording children's voices.

## Slide 2
What this session answers
Four questions, four answers - and four decisions for you at the end
SPEAK | Status & Delivery Plan | 12 July 2026
2
01
Where the project stands today
Requirements and architecture are complete and signed off internally. No production code yet - by design.
02
The programming tasks, and whether they are feasible
Eight workstreams, 44 subtasks. Seven are routine. Three carry real risk, and I name them.
03
The plan: timeline and effort at 6 h/week
284 build hours + contingency + meetings = ~60 weeks. Full Gantt with tasks and subtasks.
04
Can we record the children speaking?
Technically: yes, cheaply. Legally: only under conditions you must decide on.
Notes: Agenda. I will spend most of the time on question 3, the timeline, because that is where the difficult news is.

## Slide 3
Where the website stands today
Phase 2 of 8 complete. The thinking is done; the building has not started.
SPEAK | Status & Delivery Plan | 12 July 2026
3
2 of 8
phases complete
Requirements + Design
82
requirements specified
50 functional, 22 NFR, 10 technical
2,055
media assets inventoried
776 images, 1,279 audio files
0
lines of production code
Build starts on approval
Delivery phases
DONE
Requirements
DONE
Architecture & design
TO DO
Foundation & CI
TO DO
Accounts & access control
TO DO
Content model & importer
TO DO
Task engine
TO DO
Adaption & dashboards
TO DO
QA, release, acceptance
Why there is no code yet - and why that is the right answer
The learning material exists today as OpenSesame / OSWeb experiments on JATOS. Rewriting it as a school platform means committing to one data model for eleven different task types, to GDPR-grade access control, and to an EU deployment. Getting that wrong costs far more than the four weeks spent specifying it. The SRS and the design document are the deliverable of phases 1 and 2, and they are what makes phases 3 to 8 estimable.
Notes: Be direct: zero code is a status, not an apology. Two of eight phases are genuinely complete and they are the two that de-risk everything else.

## Slide 4
What is complete and locked
Both documents are ready for your approval today
SPEAK | Status & Delivery Plan | 12 July 2026
4
COMPLETE
Software Requirements Specification
07 July 2026
39 Must requirements (R01-R39): accounts, guards, content, 11 task types, feedback, remediation, progress
7 Should (R40-R46) and 4 Can (R47-R50)
22 non-functional requirements: GDPR, EU residency, data minimisation, hashing, rate limits, injection defence
10 technical requirements: React, Express, MySQL, JWT, importer, tests, EU hosting
Every requirement is uniquely numbered, so acceptance is measured against the numbers, not against screens
COMPLETE
Software Design Document
11 July 2026
Three-tier architecture: React SPA, Express REST API, MySQL + EU media store
Domain model, entity-relationship model, and the middleware chain (verify token > role > ownership)
The key decision: one data-driven task engine, not eleven separate activities
Security and data-protection design, four quality gates, deployment plan (Hetzner, Nuremberg)
Appendix B: full traceability matrix - every requirement mapped to a design section and a test
Decision 1 today: approve both documents as the frozen baseline. Everything below is estimated against that baseline; changing it changes the dates.

## Slide 5
What is still open - and blocks the build
Four items I need from you; two of them are on the critical path
SPEAK | Status & Delivery Plan | 12 July 2026
5
CRITICAL PATH
The complete CSV and media set
Needed by week 11 (late September)
The design assumes the Vocabulary and Grammar CSVs for Weeks 6, 10 and 12, plus all 776 images and 1,279 audio files, in the form they are held today. I have the inventory, not the working set. The importer cannot be written against a sample.
CRITICAL PATH
Confirmation that the content may be reused
Needed before week 11
The material was authored for a psychology experiment. Before it is imported into a website, I need final confirmation that you hold the rights to the images, audio and text, and that reuse in this context is permitted.
SOON
LATER
Purpose of voice recording (see question 4)
Needed before Phase 7
Whether recordings are kept or discarded changes the legal work by an order of magnitude. Discussed at the end of this deck.
Notes: The two red items are the ones that can stall the project. Everything else I can work around.

## Slide 6
The programming work, broken down
Eight workstreams, 44 subtasks, 284 estimated build hours
SPEAK | Status & Delivery Plan | 12 July 2026
6
Chart: 
| P7 QA, release & acceptance | P6 Dashboards & administration | P5 Adaption, resume & responses | P4 Remaining nine task types | P3 Task engine + types A and B | P2 Content model & importer | P1 Accounts & access control | P0 Foundation, Docker & CI
Build hours | 30 | 44 | 24 | 52 | 36 | 42 | 38 | 18
Where the hours actually go
Task engine + task types + adaption: 112 h (39%)
Security, accounts and guards: 38 h (13%)
Content importer: 42 h (15%)
Teacher and admin surface: 44 h (15%)
Plumbing, QA and release: 48 h (17%)
The design decision that saves the project
Eleven task types are not eleven applications. Every one of them reduces to the same shape: a stimulus, some options, a correct option, and feedback. So the system is one generic engine plus eight small presentation components.
Building them separately would roughly double P3 and P4 - about 100 extra hours, or five more months at this rate.

## Slide 7
Feasibility: is all of this actually buildable?
Yes - by one developer, with three genuine risks. Ratings are mine, and I stand behind them.
SPEAK | Status & Delivery Plan | 12 July 2026
7
Programming task
Assessment
Risk
Accounts, roles, route and role guards
Standard web work. Well-understood patterns, fully specified in the SDD.
LOW
Content importer (CSV + 2,055 assets)
Eleven task types, each with its own CSV columns. The mapping is unknown until I see the real files.
HIGH
Generic, data-driven task engine
The central architectural bet. If it holds, everything is cheap. Proven or disproven in week 25.
MEDIUM
The nine remaining task types
Volume, not difficulty - once the engine exists. Two exceptions below.
LOW
Storybook (A) and Memory (U)
Neither is a simple question-and-answer trial. The engine needs a narrative mode and a recall mode.
MEDIUM
Audio-first UI on tablets
iPad Safari will not play audio without a user tap. A reading-free child UI depends on getting this right.
MEDIUM
Remediation, scoring, resume
Server-side rules, cleanly isolated and unit-testable. Nothing novel.
LOW
Teacher and admin dashboards
Aggregation queries and charts. Routine.
LOW
Recording children's speech (R47)
Trivial to build. The risk is legal, not technical.
HIGH
Delivering all of it at 6 hours a week
This is the real constraint. Not the code.
HIGH
Verdict: every requirement in the SRS is buildable with this stack. Nothing needs to be dropped for technical reasons.

## Slide 8
The three risks that can actually hurt us
And what is already in the plan to contain them
SPEAK | Status & Delivery Plan | 12 July 2026
8
1
The CSV files are not as regular as they look
Appendix A of the design document says every task type reduces to one trial model. That claim is based on the file inventory, not on eleven parsed files. If Grammar's G1/G2/V_3 columns diverge sharply from Vocabulary's, the importer grows and Phase 2 slips.
Mitigation: weeks 11-12 are a CSV survey - I map all eleven column sets before writing a single line of parser. If it goes badly, we find out in September, not in March. A two-day spike on the real files before we start would sharpen this estimate considerably.
2
The one-engine bet does not fully hold
Storybook (A) is a narration, not a question. Memory / suitcase (U) is a multi-item recall, not a single choice. Both are already flagged and budgeted, but if a third type also refuses the model, the saving described on the previous slide starts to erode.
Mitigation: Phase 3 deliberately builds the engine plus the two most different types (A and B) first. By week 25 - January - we will know whether the abstraction survives contact with real content, with most of the budget still unspent.
3
Six hours a week has no slack in it
One developer, six hours. A week of illness, a school holiday, or a client decision that takes three weeks to arrive moves the end date by exactly that much. There is no second person to absorb it.
Mitigation: an eight-week contingency buffer is already inside the 60-week figure, the work is phase-gated so a partial system is always demonstrable, and the delivery options on slide 16 let you buy time back with scope or with hours.

## Slide 9
The effort model
Everything that follows is arithmetic on these five numbers. If you disagree with a number, say so now.
SPEAK | Status & Delivery Plan | 12 July 2026
9
6.0 h
contracted per week
One developer
- 0.5 h
meetings & reporting
45 min every 2 weeks
= 5.5 h
net build time / week
The real throughput
327 h
total build effort
284 h + 15% contingency
60 weeks
to client acceptance
~14 months
1
What is inside the 284 hours
Writing the code, writing its tests, writing the database migrations, and reviewing it. Under the design document's Definition of Done, a feature is not done until its tests pass and the traceability matrix is updated - so testing is not a separate line item, it is inside every estimate.
2
What the 15% contingency covers
Unknowns in the CSV files, tablet audio quirks, dependency upgrades, and the ordinary re-work of a first build. It does not cover new requirements. It does not cover a scope change.
3
What would break this model
Late content, late decisions, or new requirements. A decision that takes three weeks costs three weeks - it does not cost a phone call, because there is no parallel work to switch to.
Meetings are inside the six hours, not on top of them. Every hour we spend talking is an hour not spent building - which is why the cadence on slide 14 is deliberately lean.

## Slide 10
Project timeline: 13 July 2026 - 5 September 2027
One developer, 6 hours a week. 60 weeks to client acceptance.
SPEAK | Status & Delivery Plan | 12 July 2026
10
Jul '26
Sep '26
Nov '26
Jan '27
Mar '27
May '27
Jul '27
Sep '27
Workstream
Effort
Phase 0 Foundation, Docker & CI
18 h
W1-3
Phase 1 Accounts & access control
38 h
W4-10
Phase 2 Content model & importer
42 h
W11-18
Phase 3 Task engine + types A, B
36 h
W19-25
Phase 4 The nine remaining task types
52 h
W26-34
Phase 5 Adaption, resume & responses
24 h
W35-38
Phase 6 Dashboards & administration
44 h
W39-46
Phase 7 QA, security & production release
30 h
W47-52
Contingency buffer & client acceptance
43 h
W53-60
Foundation & release
Security & accounts
Content pipeline
Task engine & task types
Reporting
Buffer
Notes: This is the headline. Sixty weeks. If that is unacceptable, slide 16 gives you three ways to change it - and all three cost something.

## Slide 11
Tasks and subtasks: Phase 0 - Phase 3
July 2026 to January 2027 · weeks 1-25 · 134 build hours
SPEAK | Status & Delivery Plan | 12 July 2026
11
Jul '26
Aug '26
Sep '26
Oct '26
Nov '26
Dec '26
Jan '27
Subtask
Effort
P0
Repo, React + Vite, Express skeleton, ESLint
4 h
P0
Docker Compose: API, MySQL, media store
4 h
P0
CI pipeline - Gate 1 (lint, unit, secret scan)
4 h
P0
Migration framework + initial schema
3 h
P0
EU staging server, TLS, first deployment
3 h
P1
Accounts schema: users, classes, students
4 h
P1
Teacher registration + bcrypt + JWT login (R01, R02)
6 h
P1
Admin login + teacher account CRUD (R03, R08)
6 h
P1
Access codes: generate, hash, unique, regenerate (R06)
5 h
P1
Student code-only login + scoped session (R04)
4 h
P1
Middleware chain, rate limit, error handler (R14-R16)
7 h
P1
AuthContext, ProtectedRoute, RoleRoute, nav filter (R11-R13)
6 h
P2
Content schema: modules, tasks, trials, media, config
5 h
P2
CSV survey - map all 11 task-type column sets [RISK 1]
8 h
P2
CSV parser + normaliser onto one trial model (TR07)
12 h
P2
Validator: assets exist, correct option, known type
6 h
P2
Content versioning, publish, import report (R42)
6 h
P2
Admin content-import page + upload (R09)
5 h
P3
Content delivery endpoints for the player (R20)
4 h
P3
Media controller: authorised serving, signed URLs (NFR13)
5 h
P3
Media preload + iPad audio-unlock gate (R29, NFR19)
7 h
P3
TaskPlayer engine: trial loop, 2 attempts, feedback (R30, R31)
10 h
P3
StorybookTask - type A (R21)
5 h
P3
AudioImageTask - type B (R22)
5 h
Milestone at week 25 (early January): a child logs in with a code and plays a real, imported task end to end. This is the moment the architecture is proven.

## Slide 12
Tasks and subtasks: Phase 4 - acceptance
January to September 2027 · weeks 26-60 · 150 build hours + buffer
SPEAK | Status & Delivery Plan | 12 July 2026
12
Jan '27
Feb '27
Mar '27
Apr '27
May '27
Jun '27
Jul '27
Aug '27
Sep '27
Subtask
Effort
P4
AudioChoiceTask - types F_1, F_2 (R23)
7 h
P4
PictureChoiceTask - type T (R24)
5 h
P4
YesNoReflectionTask - type R (R25)
5 h
P4
GrammarArticleTask - types G1, G2, V_3 (R26)
14 h
P4
MemoryTask (suitcase) - type U [RISK 2]
10 h
P4
TeachingReflectionTask - types AT, AV, AX (R28)
8 h
P4
Cross-type polish + real-tablet pass
3 h
P5
attempts + responses tables, response capture API (R33)
5 h
P5
Server-side scoring + attempt completion (R34)
5 h
P5
Mistake counting, threshold, adaption task C (R32)
8 h
P5
Resume an interrupted module (R35, NFR20)
6 h
P6
Class and student management screens (R05-R07)
8 h
P6
Assign a module to a class or a student (R19)
6 h
P6
Progress aggregation endpoints (R36, R40)
6 h
P6
Teacher dashboard + charts (R36, R40)
8 h
P6
Results page: filters, sort, per-task drill-down (R37, R41)
8 h
P6
Module reset, confirmations, input validation (R43-R46)
4 h
P6
Print and CSV export of results (R45, R48)
4 h
P7
Playwright end-to-end suite (TR09)
8 h
P7
Security checklist, rate limits, error-leak audit
5 h
P7
Tablet, browser and child-usability pass (NFR16-NFR18)
4 h
P7
Interruption test + backup-restore rehearsal
4 h
P7
Traceability matrix complete - Gate 3
4 h
P7
Production deploy (Hetzner EU), blue/green, runbook
5 h
--
Contingency, defect fixing, acceptance walkthrough R01-R39
43 h
Optional items (R47-R50: recording, gamification, multi-language) are deliberately not on this chart. They are additive, and are quoted separately.

## Slide 13
Milestones: what you will see, and when
Nine points at which there is something real to show you
SPEAK | Status & Delivery Plan | 12 July 2026
13
M1
M2
M3
M4
M5
M6
M7
M8
M9
M1
W3 · 2 Aug 26
The empty shell runs on an EU staging server, behind HTTPS
M2
W10 · 20 Sep 26
All three logins work. A teacher cannot see another teacher's class.
M3
W18 · 15 Nov 26
Weeks 6, 10 and 12 imported. All 2,055 media files resolve.
M4
W25 · 3 Jan 27
A child plays a real task end to end. The engine is proven.
M5
W34 · 7 Mar 27
All eleven task types playable
M6
W38 · 4 Apr 27
Remediation, resume and full response capture working
M7
W46 · 30 May 27
Teacher and administrator dashboards complete
M8
W52 · 11 Jul 27
Release candidate. Gate 3 passed.
M9
W60 · 5 Sep 27
Client acceptance: R01-R39 demonstrated one by one. Go-live.
Each milestone is a working, deployed increment - not a document. If a milestone slips, you will hear it at the fortnightly meeting, not at the end.

## Slide 14
Meetings - inside the six hours, on the schedule
0.5 h per week on average, ~33 hours over the project, already deducted from build time
SPEAK | Status & Delivery Plan | 12 July 2026
14
Fortnightly progress sync
45 min
Weeks 1-60 · ~30 sessions · 22.5 h
Screen-share of what runs. Blockers. Decisions needed in the next fortnight.
Phase gate review
60 min, at each milestone
M1-M8 · 8 sessions · 8 h
Demo of the milestone against the requirement numbers it satisfies. Go / no-go for the next phase.
Content workshop
90 min, weeks 11-12
1 session · 1.5 h
With whoever authored the CSVs. I walk through the column mapping for all eleven task types before I write the parser.
Acceptance walkthrough
Half day, week 60
1 session · 4 h (from buffer)
R01 to R39 demonstrated one by one against the traceability matrix. Signed off, or not.

## Slide 15
Question 4
Can we record
the children speaking?
Short answer: the code is about 26 hours. The consent, the DPIA and the retention policy are the actual project - and they are yours, not mine.
SRS R47 (Can) · NFR07 · NFR02 (data minimisation) · NFR03 (erasure)
SPEAK | Status & Delivery Plan | 12 July 2026
15

## Slide 16
Recording: the technical side is the easy side
Everything below is standard browser capability and is already provided for in the design
SPEAK | Status & Delivery Plan | 12 July 2026
16
Capture in the browser
FEASIBLE
The MediaRecorder and getUserMedia APIs work in Chrome, Edge, Firefox and Safari 14.1+, which covers the iPad. HTTPS is required - we have it (NFR06). The browser shows an explicit microphone prompt; a child cannot be recorded silently.
Storage, encryption, deletion
FEASIBLE
Upload via the existing Multer path, encrypt at rest in the object store, key held in the platform secret store. Playback only through the authorised media controller (NFR13). Deleted in the same transaction as the student account (NFR03, NFR07). All already designed.
Automatic scoring of pronunciation
NOT IN v1
This is the part people assume is included. It is not. Speech recognition on German child speech is unreliable, and every practical ASR service is hosted outside the EU - which breaks NFR01 on its own. Recording therefore means capture and human listening, not automatic marking.
Effort if approved
~26 h
Capture hook 8 h, upload and encryption endpoint 6 h, teacher playback UI 5 h, consent gating and admin switch 4 h, cascade deletion and tests 3 h. Additive - it does not sit on the critical path, and would follow Phase 7.
None of this is hard. That is exactly why it is dangerous - it is easy to build something you are not allowed to run.

## Slide 17
Recording: the legal side is the hard side
I am a developer, not a lawyer. This is what I know I cannot ignore - your DPO must confirm it.
SPEAK | Status & Delivery Plan | 12 July 2026
17
1
It undoes the platform's best privacy property
Today a child is a display name and a hashed access code, and nothing else (NFR02). A recording of that child's voice is directly identifying. Adding it is not a feature toggle; it changes what kind of system SPEAK is.
2
Consent must come from the parent, in writing, per child
Under Art. 8 GDPR a primary-school child cannot give valid consent. In Germany you need documented guardian consent, obtainable before the child ever sees a microphone prompt - and revocable at any time, with deletion.
3
A DPIA is very likely mandatory
Art. 35: systematic processing of children's data, in a school, including audio. Assume the answer is yes. The school's or the Land's data-protection officer signs it, not me.
4
Purpose limitation and retention must be written down before the code runs
Why is the recording kept? For how long? Who may listen? What happens at the end of the school year? If we cannot answer these in one sentence each, we should not be storing anything.
5
A child who opts out must still be able to do the task
Recording can never be a condition of learning. The speaking task must have a non-recording path, or it cannot be assigned to a class at all.
The legal work is measured in months of school and authority process, not in hours of mine. It cannot start after the code is written.

## Slide 18
Recording: my recommendation
The question you actually have to answer is not technical
SPEAK | Status & Delivery Plan | 12 July 2026
18
Option A - Transient
Record, play back to the child, discard.
The child hears themselves say the word and compares it with the model. Nothing leaves the browser. Nothing is stored. No DPIA, no parental consent form, no retention policy, no erasure obligation - because there is no personal data.
Effort: ~10 h. Could ship in the buffer.
Option B - Retained
Store the recording for the teacher to listen to.
The teacher can review a child's pronunciation later, and the recordings can be used for research or assessment. Everything on the previous slide now applies: guardian consent, a DPIA, a retention period, an opt-out path, and a deletion route.
Effort: ~26 h of code, plus your legal process.
What I recommend
Keep R47 as a Can requirement and leave it off the critical path.
Build Option A first. It delivers most of the pedagogical value - a child hearing themselves - at a tenth of the governance cost.
Build Option B behind a feature flag that is OFF by default, and enable it per class only once the DPIA is signed and the consent forms are in. The switch belongs to the administrator, not to the code.
Decision 2 today: is the recording for the child (transient) or for the adults (retained)? Every other question about R47 follows from that one, and I cannot answer it for you.

## Slide 19
Four decisions, today
Every one of them is on the critical path.
1
Approve the SRS and the design document as the frozen baseline.
2
Decide the purpose of voice recording: transient (Option A) or retained (Option B).
3
Commit a date for handing over the complete CSV and media set, and confirmation of reuse rights. Needed by week 11 (late September).
4
Name one person on your side who can make a decision inside a fortnight, and fix the fortnightly slot.
Janaki Badu · Full-Stack Web Developer · SPEAK · 12 July 2026
Notes: Close by asking for the decisions in order. Do not leave the room without 1, 2 and 5.